# Project Closeout Template

Last updated: 2026-10-08 · Owner: BSA Manager

- Purpose: close an epic or project properly: compare results with objectives, hand over deliverables and support, update the documentation, give every open item an owner, capture lessons learned, and get sign-off. Keep it to 1 to 3 pages.

- Who uses it: the BSA who led the epic writes it; the Manager reviews it; the business owner and checkers sign; whoever takes over a deliverable confirms the handover.

- When: within 5 working days after the last child issue is Done. For a tool or system change, after go-live and the first clean production cycle. Use it for every epic: tariff action responses, tool enhancements, transition work (exports and reporting backlog items), e2open workstreams. Module M4.

## How to fill this in

Text in [square brackets] is a prompt: replace it. [COMPANY: ...] is a company-specific value.

- Copy the objectives and measures from the requirements (docs/templates/bsa/02-requirements.md) or the epic description. Measure the actual results with data, not impressions.

- List every deliverable with its location and who supports it from now on.

- Work through the documentation checklist and link each updated page.

- Turn anything unfinished into a Jira issue with an owner and a date. No "TBD" owners.

- Run a 30-minute lessons-learned session with the people involved (agenda below). Record Keep, Stop and Start, each with evidence and an action.

- Send it for sign-off. Close the epic only after sign-off.

## Template

### 1. Header

| Field | Entry |
| --- | --- |
| Project or epic | [Name] |
| Jira key | [Key] |
| Dates | Start [date]; planned end [date]; actual end [date] |
| Lead (maker) | [Name] |
| Checkers | [Names] |
| Business owner | [COMPANY: role] |
| Related documents | [Intake, requirements, process map, data map, UAT plan, change requests] |

### 2. Summary

[3 to 5 sentences: what was delivered, against which objective, the key result, and what is still open.]

### 3. Objectives vs results

| Objective | Measure | Target | Actual | Met? | Notes |
| --- | --- | --- | --- | --- | --- |
| [O1] | [Metric] | [Target] | [Actual, with source] | [Yes, Partly, No] | [Why, if not met] |

### 4. Scope delivered

- Delivered as planned: [items]

- Delivered with changes: [item, what changed, who agreed]

- Not delivered: [item, why, and where it went: Jira key or "dropped, agreed by [name] on [date]"]

### 5. Delivery measures

| Measure | Planned | Actual | Comment |
| --- | --- | --- | --- |
| End date | [ ] | [ ] | [ ] |
| Effort (hours) | [Estimate] | [Actual, if tracked] | [ ] |
| Defects found in UAT | n/a | [n] | [ ] |
| Defects found after go-live or release | 0 | [n] | [ ] |
| Checker findings before release | n/a | [n] | [Types of finding] |

### 6. Deliverables and handover

| Deliverable | Location | New owner | Support arrangement | Accepted (name, date) |
| --- | --- | --- | --- | --- |
| [Brief, model, tool version, report, SOP, data map] | [Link] | [Name or role] | [Who to call; how issues are logged] | [ ] |

### 7. Controls evidence

| Release | Maker | Checker | Evidence link | Date |
| --- | --- | --- | --- | --- |
| [Brief v1.0, model v1.2, CR, cost input file] | [ ] | [ ] | [Jira comment or sign-off block] | [ ] |

### 8. Documentation updated

- ☐ Tool docs (docs/templates/knowledge/tool-doc.md): new version number and change-history line.

- ☐ Process SOPs (docs/templates/knowledge/process-sop.md): steps, controls and exceptions that changed.

- ☐ OneNote: pages updated, links checked, superseded pages marked "superseded by [page]".

- ☐ Anki: company-specific cards added or corrected (docs/templates/knowledge/anki-card-writing-guide.md); list them.

- ☐ Trackers workbook: Tool Inventory row and glossary terms updated.

- ☐ Process maps: the to-be is now the as-is; the old version is archived.

- ☐ Data mapping specs and value maps reflect what was built.

- ☐ Jira: every child issue is closed or moved, with components and labels correct.

- ☐ e2open: anything the project team needs (data map changes, tool disposition notes) has been sent to [COMPANY: e2open project lead].

- ☐ Evidence is retained per [COMPANY: records retention policy].

### 9. Open items and owners

| ID | Item | Owner | Due | Jira key | Risk if not done |
| --- | --- | --- | --- | --- | --- |
| OI-1 | [What is left] | [Name] | [Date] | [Key] | [Consequence] |

### 10. Lessons learned (Keep, Stop, Start)

| Type | Lesson | Evidence | Action | Owner |
| --- | --- | --- | --- | --- |
| Keep | [What worked and should be repeated] | [Fact or number] | [How to make it standard] | [Name] |
| Stop | [What caused rework, delay or risk] | [ ] | [ ] | [ ] |
| Start | [What to try next time] | [ ] | [ ] | [ ] |

Session agenda (30 minutes):

- Timeline of facts (5 minutes): what happened, when, from the Jira history.

- Keep (10 minutes): what worked, and why.

- Stop and Start (10 minutes): what didn't work, and what to try instead.

- Actions (5 minutes): pick no more than 3, each with an owner and a date.

Rules: talk about the process, not the person. Back each lesson with a fact. Make each action specific. Actions land in an SOP change, a Jira issue, an Anki card, or a template change request to the Manager (the Manager owns these templates).

### 11. Sign-off

| Role | Name | Decision | Date | Comments |
| --- | --- | --- | --- | --- |
| Business owner | [ ] | [Accepted, Accepted with open items, Not accepted] | [ ] | [ ] |
| New owner of the deliverables | [ ] | [Handover accepted] | [ ] | [ ] |
| Checker | [ ] | [Controls evidence complete] | [ ] | [ ] |
| Manager | [ ] | [Approved to close] | [ ] | [ ] |

## Filled example (short)

Closeout for the hypothetical "Tariff action: Country X steel fasteners" epic (see the example in docs/templates/bsa/01-intake-request.md). Lead: Hire A, with Hire B. Checkers: Senior (brief), Manager (model). Business owner: [COMPANY: Pricing lead].

Summary. The checked brief and the $ impact were both delivered before the pricing meeting. Of the 140 candidate items, 138 were confirmed in scope; the Senior's review moved 2 borderline items out of heading 7318, and their classification was corrected through change requests before the effective date. The $ summary arrived 40 minutes late because the volume forecast came in a day late. Three items remain open.

| Objective | Measure | Target | Actual | Met? | Notes |
| --- | --- | --- | --- | --- | --- |
| O1 Checked brief released early | Release time | Thu 12:00 | Thu 11:30 | Yes | 1 checker finding (stacking wording), closed |
| O2 $ impact checked and sent before pricing | Send time | Fri 08:00 | Fri 08:40 | Partly | Forecast arrived Wed 16:00 instead of 12:00 |
| O3 No material errors after release | Errors found in 30-day look-back | 0 | 0 | Yes | Look-back done by Hire A, checked by the Senior |
| O4 Classification right before the effective date | Borderline items resolved | 6 of 6 | 6 of 6 | Yes | 2 changed via change requests |

| Deliverable | Location | New owner | Support arrangement | Accepted (name, date) |
| --- | --- | --- | --- | --- |
| Tariff-Impact Brief v1.0 | [COMPANY: briefs folder] | Hire A | Updated if CBP issues further guidance | [COMPANY: Pricing lead], [date] |
| Tariff-Impact Model v1.2 | [COMPANY: model folder] | Hire B | Feeds the next standard cost cycle | Manager, [date] |
| Rate-table rows with effective dates | [COMPANY: name of std-cost tool] | Hire B | Normal tool support | Manager, [date] |

| ID | Item | Owner | Due | Jira key | Risk if not done |
| --- | --- | --- | --- | --- | --- |
| OI-1 | Watch CBP CSMS for guidance on the in-transit terms | Hire A | Effective date + 10 working days | [key] | Wrong duty basis on in-transit goods |
| OI-2 | Include the new duty in the next standard cost update (maker-checker) | Hire B | [COMPANY: next cycle date] | [key] | Standard cost understated; PPV inflated |
| OI-3 | Check the last 90 days of entries for the 2 reclassified items | Hire A, with the Senior | [date] | [key] | Unflagged errors on past entries |

| Type | Lesson | Evidence | Action | Owner |
| --- | --- | --- | --- | --- |
| Keep | Split WHAT and $ into linked stories on day 1 | Handoff took 15 minutes; no clarification rounds | Already in the intake routing rule; keep it | Both hires |
| Stop | Matching items in Excel | Leading zeros lost; 3 items missed in the first pass | Saved SQL matching query in [COMPANY: code repository]; added to the Research SOP | Hire A |
| Start | Ask for volume forecasts at intake, not on day 2 | Forecast arrived late; $ summary 40 minutes late | Add "volume forecast" to the Standard Cost SOP intake step; ask the Manager whether to add it to the intake template | Hire B |

Documentation updated: Research SOP draft (in-transit step and SQL matching); 4 new Anki cards (Chapter 99 stacking basics, in-transit terms, reading an annex, HTS leading zeros); Tool Inventory unchanged.

## Quality checklist before you send

- ☐ Every objective has a measured actual result with its source, and an honest Met, Partly or No.

- ☐ Anything not delivered says why, and where it went.

- ☐ Every deliverable has a location, a new owner, a support arrangement and an acceptance.

- ☐ Every release has maker-checker evidence linked.

- ☐ The documentation checklist is complete, with links; Anki cards are listed.

- ☐ Every open item has one owner, a date, a Jira key and the risk if not done.

- ☐ Lessons have evidence and no more than 3 actions, each with an owner; no blame.

- ☐ Anything the e2open project needs has been sent.

- ☐ Sign-off is recorded before the epic is closed.