# Weeks 1-2 Schedule

Last updated: 2026-10-08 · Owner: BSA Manager

- Purpose: the hour-by-hour plan for the first two weeks, plus the Manager's to-do list for the week before the start date.

- Who uses it: the Manager (prep, sessions, 1:1s), the Senior (four sessions, office hours including Hire A's USMCA test-out, one analytics review), and both hires (what to do in every block, and which file to open).

- When: prep runs Mon 10/12 to Fri 10/16. Week 1 is Mon 10/19 to Fri 10/23 and Week 2 is Mon 10/26 to Fri 10/30. From Week 3, the roadmap (Section 3) and the standard week (Section 5) in docs/01-30-60-90-plan.md take over.

## Weeks 1–2 at a glance

One row per day; the day tables below have the times, files and outputs. "Hire A:" and "Hire B:" items run in parallel; everything else is both hires together. From Day 2, every day starts with 15 min of Anki and ends with a 15-minute slot at 16:45 (the daily wrap; on Fridays, next week's plan in Planner). Trainer time counts a shared session once, as in "Trainer hours" below.

### Week 1: Mon 10/19 - Fri 10/23

| Day | Morning | Afternoon | Trainer time |
| --- | --- | --- | --- |
| Day 1, Mon 10/19 | HR orientation, laptop and sign-ins (08:00-12:00) | Manager welcome and plan walkthrough; meet the Senior; access check; time management reading; Anki import; Day-1 wrap with the Manager | Manager 1.25 h; Senior 0.25 h |
| Day 2, Tue 10/20 | Stand-up; US customs reading. Hire A: Purchasing or Logistics shadow. Hire B: business overview skim, then Oracle cost data | Manager: trade systems landscape (1.5 h); trade systems primer and landscape diagram v1; analytics setup | Manager 1.50 h |
| Day 3, Wed 10/21 | Stand-up; Exercise 1; Manager: ways of working, Jira, Planner and time management (1 h); Planner tasks, Jira stories, first weekly plan | Senior S1, US customs I (1.5 h); entry flow v2 and 5 cards. Hire A: business reading. Hire B: cost checklist mapped to Oracle data | Manager 1.00 h; Senior 1.50 h |
| Day 4, Thu 10/22 | Stand-up; Exercise 2. Hire A: primer pre-read. Hire B: Finance shadow on the cost calendar. Both: entry packet pre-read | Hire A: business orientation with the Manager (45 min). Hire B: standard cost extract. Senior: data landscape tour (30 min). Hire A: origin and kit notes. Hire B: primer pre-read. Senior office hours (30 min); cards | Manager 0.75 h; Senior 1.00 h |
| Day 5, Fri 10/23 | Entry packet; Senior S2, US customs II (1.5 h); self-report and W2 plan sent by 11:30; 5 cards | 1:1s with the Manager (Hire A 13:00, Hire B 13:45). Hire A: e2open reading. Hire B: cost-element comparison. Exercises 1-2 retro; buffer; W2 plan in Planner | Manager 1.50 h; Senior 1.50 h |

Week 1 total: Manager 6.00 h, Senior 4.25 h.

### Week 2: Mon 10/26 - Fri 10/30

| Day | Morning | Afternoon | Trainer time |
| --- | --- | --- | --- |
| Day 6, Mon 10/26 | Monday confirm with the Manager (15 min); Canada primer reading; Exercise 3 | Mexico primer reading. Hire A: business orientation II with the Manager (30 min). Hire B: one-item PO-to-cost trace. Track pre-reads for Wednesday's shadows | Manager 0.75 h |
| Day 7, Tue 10/27 | CAD and pedimento pre-read; Senior S3, Canada and Mexico customs (1.5 h); US/CA/MX comparison table and 5 cards | Manager: AS400 trade data-flow walkthrough (1.5 h); data-flow v1 and 5-row mini data map; finish and post Exercise 3 | Manager 1.50 h; Senior 1.50 h |
| Day 8, Wed 10/28 | Stand-up; classification basics on 5 practice items. Hire A: shadow a real Research item. Hire B: shadow a real standard cost or variance item | Manager: BSA craft intro, intake and Jira stories (45 min); shadow write-up. Hire A: USMCA oral test-out with the Senior (15 min) while Hire B starts Exercise 4. Senior office hours (15 min); Exercise 4 | Manager 0.75 h; Senior 0.50 h |
| Day 9, Thu 10/29 | Finish and post Exercise 4; Manager: custom tools kickoff (1 h); start the Tool Inventory | Senior S4, USMCA origin and classification (1.5 h); Senior analytics review of Exercises 1-3 (30 min); teach-back prep. Hire A: kit item (GRI 3(b)). Hire B: Exercise 3 stretch on the cost extract | Manager 1.00 h; Senior 2.00 h |
| Day 10, Fri 10/30 | Tool Inventory; teach-back rehearsal; first Friday teach-back with the Manager (30 min); self-report and W3 plan sent by 11:30; fix teach-back errors | 1:1s with the Manager (Hire A 13:00, Hire B 13:45). Hire A: tool inventory, then research monitoring set-up. Hire B: e2open reading, then the PPV example. Buffer; W3 plan in Planner | Manager 2.00 h |

Week 2 total: Manager 6.00 h, Senior 4.00 h.

## How to read this schedule

- Times assume an 08:00-17:00 day with lunch 12:00-13:00. Shift every block to fit [COMPANY: core hours and time zone]; keep the order.

- A row with no prefix means both hires together. Rows that start with "Hire A:" or "Hire B:" run at the same time, in parallel.

- Lead values: Manager, Senior, HR (HR or IT runs it), Shadow (the hire sits with someone doing real work), Hires (both hires together, no trainer), Self-study (the hire works alone from the named file).

- Files that are not OneNote pages (the Anki deck, practice data, model template, trackers workbook) are in the onboarding folder ([COMPANY: team onboarding folder on SharePoint/Teams]), linked from OneNote 00 Start Here.

- Output is what exists in the hire's OneNote section (or Jira or Planner) at the end of the block. If the output is missing, the block is not done; carry it to the Friday self-report.

- Every self-study block names a file. If that file says something different from this schedule, follow the file and add a note to the question log.

- Daily routine for the hires: 15 min of Anki first thing, and a 15-min wrap at 16:45 (question log, notes, tomorrow's top-3). Method: docs/05-time-management.md.

- If system access is late, use the fallback plan in docs/04-access-request-checklist.md. Do not drop the block.

## Before day 1: Manager checklist (week of Mon 10/12)

Today is Thu 10/08. Access requests are the long pole, so send them before the weekend if you can.

### By Mon 10/12

- ☐ Submit every request marked "Day 1" or "Week 1" in docs/04-access-request-checklist.md for both hires. Put ticket numbers in its tracking table (on its OneNote copy once the notebook is set up); the hires copy that table into their own Access tracker pages on Day 1.

- ☐ Submit the Week 2 requests too: Oracle inquiry for Hire A, AS400 inquiry for both, and read access to the shared drives or SharePoint folders where the custom tools live.

- ☐ Confirm with HR the time and place of [COMPANY: HR orientation] on Mon 10/19 (the schedule assumes 08:00-12:00).

- ☐ Ask HR whether Hire B, who already knows the business, can take a shorter orientation session. If so, Hire B uses the spare morning for the access check and the Oracle cost-data self-study (Tue 10:30 block).

- ☐ Confirm laptops come with Outlook, Teams, OneNote, Excel (Power Query is built into Excel for Windows), VPN and MFA.

- ☐ Book the shadow hosts (they are not trainers, but it is their time):

  - [COMPANY: Purchasing or Logistics contact]: Hire A, Tue 10/20 10:30-12:00.

  - [COMPANY: Finance cost accountant]: Hire B, Thu 10/22 10:00-11:00.

  - [COMPANY: current Research process runner]: Hire A, Wed 10/28 10:00-12:00.

  - [COMPANY: current Standard Cost process runner or Finance cost accountant]: Hire B, Wed 10/28 10:00-12:00.

- ☐ Book 30-minute intro meetings for Hire A with each group in [COMPANY: stakeholder list], spread across W3-W4 (not on Wed 11/11, the worksheet due date). Hire A updates the stakeholder map after each one (A30-9).

### By Wed 10/14

- ☐ Run python3 build/build.py (or take the files from dist/) so the Word versions in dist/docs/ are current.

- ☐ Set up the OneNote team notebook with the sections from README.md: 00 Start Here, 01 Check-ins, 02 Primers, 03 Templates, 04 Tool Docs, 05 Process SOPs, 06 Question Log, 07 Analytics.

- ☐ Add one section group per hire ("Hire A notes", "Hire B notes") with four pages: Daily notes, Weekly plans and self-reports, Teach-backs, and Access tracker (left empty; the hire copies the tracking table from the access checklist into it on Day 1). In section 06 Question Log, add one page per hire ("Hire A questions", "Hire B questions"): that page is the hire's question log.

- ☐ Paste these pages first (Word: Ctrl+A, Ctrl+C, then paste into OneNote): program at a glance, 30/60/90 plan, this schedule, access checklist and time management (00 Start Here); check-ins and scorecards (01 Check-ins); the customs primer and the trade systems primer; practice exercises; and the templates folder.

- ☐ The answer key is built to dist/trainer-only/answer-key.docx. Keep it in [COMPANY: trainer-only location], never in the notebook or the onboarding folder, and never give the hires it or data/analytics/generate_practice_data.py before the day-30 review. The Senior uses it on Thu 10/29.

- ☐ Copy to the onboarding folder ([COMPANY: team onboarding folder on SharePoint/Teams]): dist/BSA-Onboarding.apkg, dist/anki/BSA-Onboarding-cards.csv, dist/Practice-Data.xlsx, the dist/practice-data/ folder, dist/Tariff-Impact-Model-Template.xlsx, dist/BSA-Onboarding-Handbook.docx, dist/docs/, and dist/BSA-Onboarding-Trackers.xlsx (the only file both hires can edit). Never copy dist/trainer-only/. Link the folder and the workbook from 00 Start Here (AR-14, live Day 1).

- ☐ In its Tool Inventory tab, overwrite the placeholder rows (T-01 to T-15) with every custom tool you know of: tool name, stack, and where it lives. This list is the input to the Thu 10/29 split. Leave the other columns for the hires.

- ☐ Jira: add both hires to [COMPANY: Jira project] and create an empty epic for each, "Onboarding - Hire A" and "Onboarding - Hire B". They add their own stories on Wed 10/21.

- ☐ Planner: create a plan called "BSA Onboarding" with buckets This week, Doing, Waiting or Blocked, and Done. Add both hires and the Senior.

- ☐ Anki: confirm IT has installed Anki desktop (from apps.ankiweb.net, through [COMPANY: software approval process]) on both laptops. Test-import dist/BSA-Onboarding.apkg on your own machine.

- ☐ Decide on AnkiWeb sync. The default is off for company-specific cards unless IT approves, because sync stores the cards on an outside service.

### By Thu 10/15

- ☐ Block the Senior's calendar for the slots in the table below, plus about 1 h this week for the Senior to prepare S1-S4 (15 minutes each, using the session template in docs/03-check-ins-and-scorecards.md Section 4). Check the slots against the Senior's drawback, exports and reporting deadlines; move a session within the same week if there is a clash.

- ☐ Block your own calendar for every Manager row in the day tables, plus 2 h (W1) and 2 h (W2) of async review time. Friday 15:00-16:00 works well for reviewing the self-reports and planning the next week.

- ☐ Gather the sanitized sample documents (table below). Save them to the onboarding folder and link them from OneNote 03 Templates.

| Senior slot | Week | Session | Hours |
| --- | --- | --- | --- |
| Mon 10/19 14:00-14:15 | W1 | Meet the Senior | 0.25 |
| Wed 10/21 13:00-14:30 | W1 | S1: US customs fundamentals I | 1.50 |
| Thu 10/22 13:45-14:15 | W1 | Data landscape tour | 0.50 |
| Thu 10/22 15:30-16:00 | W1 | Office hours | 0.50 |
| Fri 10/23 09:00-10:30 | W1 | S2: US customs fundamentals II (entry packet) | 1.50 |
| Tue 10/27 09:00-10:30 | W2 | S3: Canada and Mexico customs | 1.50 |
| Wed 10/28 15:00-15:30 | W2 | Hire A USMCA test-out (15 min), then office hours | 0.50 |
| Thu 10/29 13:00-14:30 | W2 | S4: USMCA origin and classification basics | 1.50 |
| Thu 10/29 14:30-15:00 | W2 | Analytics review (Exercises 1-3) | 0.50 |

### Sanitized sample documents to gather

Mask anything that identifies the company or its partners before a sample goes into the onboarding folder: IOR and EIN numbers, Canadian business number (BN) and RM account, Mexican RFC and IMMEX program number, bond numbers, broker account numbers, supplier and customer names, and unit prices if they are confidential. Keep the structure and the HTS, value, origin and duty fields readable.

| Sample | Used on | What it must show |
| --- | --- | --- |
| US broker entry packet: entry summary (CBP Form 7501), CBP Form 3461 if available, commercial invoice, packing list, bill of lading or air waybill, broker invoice [COMPANY] | Thu 10/22 pre-read; Fri 10/23 S2 | At least 3 lines with different HTS numbers, one with an extra duty line if you have one |
| Canada: one Commercial Accounting Declaration (CAD) and its invoice [COMPANY] | Tue 10/27 S3 | Tariff classification, value for duty, origin and tariff treatment fields |
| Mexico: one pedimento and its invoice [COMPANY] | Tue 10/27 S3 | Fracción and NICO, customs value, origin, and an IMMEX example if the company uses IMMEX |
| One completed Tariff-Impact example (a brief, a model, or both) from a recent tariff action [COMPANY] | Mon 10/26 pre-reads; Wed 10/28 shadows | Source, affected HTS, rates, effective date, item-level $ impact, and who reviewed it |
| Standard cost extract: 10-20 items with cost elements (material, freight, duty, other) for one cost period [COMPANY: Oracle EBS or Fusion] | Hire B from Tue 10/20 | Duty and freight visible as separate elements or rates |
| PO and receipt extract: the same items, one PO line and its receipt each [COMPANY: Oracle EBS or Fusion] | Hire B Tue 10/20, Mon 10/26 | PO price, currency, Incoterm, receipt date and quantity next to the standard cost |
| Broker entry-line extract: one month of US entry lines for the same items [COMPANY] | Hire B W3 profiling; Hire B B30-6 | Entry, line, HTS, origin, value, duty |
| PPV example: one month, a few items [COMPANY: PPV report] | Hire B Fri 10/30 | Standard vs actual, with at least one duty- or freight-driven variance |
| AS400 trade item extract: item, description, HTS per country, country of origin, USMCA indicator [COMPANY] | Tue 10/27 data-flow session | Same items as the cost extract if possible, so the hires can join them |
| Five item descriptions for classification practice, with the correct HTS kept by the Senior [COMPANY] | Wed 10/28 worksheet; Thu 10/29 S4 | One simple item, one with a material question, one kit or set |
| Company overview or product-line deck; org chart or stakeholder list [COMPANY] | Hire A, Wed 10/21 and Thu 10/22 | Product families, source countries, US/CA/MX entities |

### By Fri 10/16

- ☐ Check every access request. Escalate anything due on Day 1 that is not provisioned, using the rules in docs/04-access-request-checklist.md.

- ☐ Send both hires a welcome note with Day-1 logistics: start time, location or badge pickup, who meets them, the HR orientation slot, and lunch.

- ☐ Print a backup pack in case laptops or logins are late: the Week 1 pages of this schedule, the US sections of the customs primer, and docs/05-time-management.md.

- ☐ Read the 1:1 agenda in docs/03-check-ins-and-scorecards.md and prepare the Day-1 welcome talk, which walks through docs/01-30-60-90-plan.md.

## Week 1 (Mon 10/19 - Fri 10/23)

Week focus: M0 orientation and ways of working, M1 US customs fundamentals, M2 trade systems landscape, M3 analytics Exercises 1-2. Anki starts on Day 1.

### Day 1 - Mon 10/19

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-12:00 | [COMPANY: HR orientation]: policies, benefits, badge, plus IT laptop, MFA, email and Teams sign-in. Hire B: if HR confirms a shorter session, start the access check below early | HR | M0 | HR checklist done; can sign in to laptop, email and Teams |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-14:00 | Welcome: team purpose and stakeholders; walk through docs/01-30-60-90-plan.md; how 5-8 guided hours a week plus structured self-study works; the boundary rule (Research owns the WHAT, Standard Cost owns the $) and the maker-checker rule | Manager | M0 | Each hire writes their own day-30/60/90 goals in their OneNote section |
| 14:00-14:15 | Meet the Senior: what the Senior owns (reporting, exports, US duty drawback), office-hour slots, how to bring questions (question log), and why questions for a broker or trade counsel go through the Senior | Senior | M0 | Office-hour slots in calendar |
| 14:15-15:00 | Access check: copy the tracking table from docs/04-access-request-checklist.md into the Access tracker page in your own section; try each system due by Day 1 (AR-01, AR-02, AR-10, AR-14 onboarding folder, AR-21), mark the others "not due yet", and record each status there; send the gaps to the Manager by 15:00 | Self-study | M0 | Access tracker page filled in; gaps sent |
| 15:00-15:45 | Read docs/05-time-management.md (weekly ritual, daily top-3, intake rules, question log); set up your daily-plan page and your question-log page in section 06 Question Log, using the templates in docs/05-time-management.md | Self-study | M0 | Daily plan and question log pages in OneNote |
| 15:45-16:00 | Anki: import BSA-Onboarding.apkg from the onboarding folder (link in 00 Start Here); first review session | Self-study | M1 | Deck imported; first reviews done |
| 16:00-16:45 | Read OneNote 00 Start Here: Program at a Glance, then start Sections 1 and 3 of the 30/60/90 plan (finish them by Fri 10/23); skim the rest of this week's schedule; log anything unclear | Self-study | M0 | Week 1 questions in the question log |
| 16:45-17:00 | Day-1 wrap: blockers, first questions, Tuesday's top-3 | Manager | M0 | Top-3 for Tue written |

### Day 2 - Tue 10/20

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-08:15 | Anki daily review | Self-study | M1 | Reviews done |
| 08:15-08:30 | Stand-up (hires only): top-3, blockers, access status; post blockers and access gaps to the Manager in Teams | Hires | M0 | Blockers posted |
| 08:30-10:30 | Read the US sections of docs/primers/customs-trade-compliance-primer.md: importer of record, broker and CBP roles, the entry process, duties and fees. List new terms as you go | Self-study | M1 | 10+ terms noted; 3+ questions in the question log |
| 10:30-12:00 | Hire A: shadow [COMPANY: Purchasing or Logistics contact] on how a purchase order becomes an import (supplier, booking, broker, receipt) | Shadow | M0 | One-page "PO to receipt" note |
| 10:30-12:00 | Hire B: the business overview is a refresher: skim [COMPANY: business overview materials] for 30 minutes (no quiz; note anything new for Friday's 1:1). Then Oracle cost data: in [COMPANY: Oracle EBS or Fusion] inquiry, find one item's standard cost and its cost elements, one PO and its receipt. If Oracle is not live, use the sanitized standard cost and PO-receipt extracts | Self-study | M5C | Overview notes; note: each cost element and where it appears |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-14:30 | Trade systems landscape: what trade data the AS400 trade system holds and who uses it [COMPANY]; Oracle touchpoints (items, POs, receipts, costs); broker data exchange in US/CA/MX; the data warehouse and Power BI; the e2open GTM plan (project starts January 2027, and the hires will be core project BSAs) | Manager | M2 | Hand-drawn landscape sketch (photo into OneNote) |
| 14:30-16:00 | Read docs/primers/trade-systems-gtm-e2open-primer.md (GTM concepts and e2open); redraw the landscape with the system, the data and the owner on each box | Self-study | M2 | Landscape diagram v1 in OneNote |
| 16:00-16:45 | Analytics setup: open docs/analytics/practice-exercises.md, load Practice-Data.xlsx from the onboarding folder (or the CSV files in its practice-data folder) into Excel and Power Query, read Exercise 1 | Self-study | M3 | Data loaded; Exercise 1 questions noted |
| 16:45-17:00 | Daily wrap: question log, notes, Wednesday's top-3 | Self-study | M0 | Top-3 for Wed |

### Day 3 - Wed 10/21

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-08:15 | Anki daily review | Self-study | M1 | Reviews done |
| 08:15-08:30 | Stand-up (hires only); blockers to the Manager in Teams | Hires | M0 | Blockers posted |
| 08:30-10:00 | Analytics Exercise 1 (docs/analytics/practice-exercises.md) | Self-study | M3 | Exercise 1 file in OneNote 07 Analytics, plus 3 lines on what you learned |
| 10:00-11:00 | Ways of working: the Jira project (issue types, workflow, how a request gets logged), Planner for learning tasks, email and Teams rules, and the rituals in docs/05-time-management.md | Manager | M0 | Each hire logs one practice request in Jira using the fields in docs/templates/bsa/01-intake-request.md |
| 11:00-12:00 | Add your W1-W2 learning tasks to Planner and your onboarding stories to your Jira epic (docs/templates/bsa/07-jira-epic-story.md); draft your first weekly plan from the template in docs/05-time-management.md | Self-study | M0 | Planner tasks; Jira stories; draft weekly plan |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-14:30 | S1, US customs fundamentals I: importer of record and reasonable care; the broker's role; entry (CBP Form 3461) vs entry summary (CBP Form 7501); ACE; duties and fees (MPF, HMF); liquidation, post-summary corrections and protests | Senior | M1 | Annotated US entry flow in OneNote |
| 14:30-15:30 | Rewrite the US entry flow in your own words; write 5 Anki cards using docs/templates/knowledge/anki-card-writing-guide.md | Self-study | M1 | Entry flow v2; 5 draft cards |
| 15:30-16:45 | Hire A: business orientation self-study. Read [COMPANY: company overview or product-line deck] and list the top product families, main source countries and the US/CA/MX entities | Self-study | M0 | Business map notes |
| 15:30-16:45 | Hire B: read docs/templates/domain/standard-cost-update-checklist.md and map each step to the Oracle data you looked at on Tuesday | Self-study | M5C | Annotated checklist |
| 16:45-17:00 | Daily wrap | Self-study | M0 | Top-3 for Thu |

### Day 4 - Thu 10/22

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-08:15 | Anki daily review | Self-study | M1 | Reviews done |
| 08:15-08:30 | Stand-up (hires only); send your batched questions for the Senior's 15:30 office hours by 12:00 | Hires | M0 | Blockers posted |
| 08:30-10:00 | Analytics Exercise 2 | Self-study | M3 | Exercise 2 file plus 3 lines on what you learned |
| 10:00-11:00 | Hire A: read the classification, valuation and origin sections of docs/primers/customs-trade-compliance-primer.md (pre-read for Friday) | Self-study | M1 | Questions for S2 |
| 10:00-11:00 | Hire B: shadow [COMPANY: Finance cost accountant] on the standard cost calendar and how duty and freight rates get into standard cost | Shadow | M5C | Note: cost calendar dates and who does each step |
| 11:00-12:00 | Pre-read for S2: on the sanitized US entry packet [COMPANY], find the importer, HTS numbers, entered value, country of origin and duty lines on the 7501. Mark which fields come from our data | Self-study | M1 | Marked-up packet with 10 fields |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-13:45 | Hire A: business orientation with the Manager. Customers, suppliers, product lines, US/CA/MX entities, where margin comes from, and who the main internal stakeholders are | Manager | M0 | One-page business map |
| 13:00-13:45 | Hire B: in the sanitized standard cost extract, find duty and freight in each item's cost; list 3 questions for your next Finance touchpoint | Self-study | M5C | Annotated extract |
| 13:45-14:15 | Data landscape tour: SQL Server, the data warehouse, Power BI workspaces; what data lives where, read-only rules, where trade data shows up | Senior | M3 | Data boxes added to the landscape diagram |
| 14:15-15:30 | Hire A: second pass on the origin and marking sections of the customs primer. Note where kits and bills of material make origin harder (bring this to S4 next week) | Self-study | M1 | Kit/BOM origin notes |
| 14:15-15:30 | Hire B: read the classification, valuation and origin sections of the customs primer (pre-read for Friday) | Self-study | M1 | Questions for S2 |
| 15:30-16:00 | Senior office hours: batched questions from both question logs | Senior | M1 | Answers recorded in the question log |
| 16:00-16:45 | Turn the answered questions into Anki cards or glossary notes | Self-study | M1 | 3+ new cards |
| 16:45-17:00 | Daily wrap | Self-study | M0 | Top-3 for Fri |

### Day 5 - Fri 10/23

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-08:15 | Anki daily review | Self-study | M1 | Reviews done |
| 08:15-09:00 | Finish the entry packet mark-up; pick your 2 most important questions for S2 | Self-study | M1 | Packet ready; 2 questions |
| 09:00-10:30 | S2, US customs fundamentals II: walk the sanitized entry packet line by line. Classification (HTSUS structure, the General Rules of Interpretation), valuation (transaction value and additions), country of origin and marking, recordkeeping. What data the team owns vs what the broker keys in, and how the team audits broker filings | Senior | M1 | Corrected packet mark-up; "our data vs broker data" list |
| 10:30-11:30 | Friday self-report (the 5 prompts in docs/03-check-ins-and-scorecards.md Section 5) and draft W2 weekly plan (template in docs/05-time-management.md); send both to the Manager by 11:30 | Self-study | M0 | Self-report and W2 plan sent |
| 11:30-12:00 | Write 5 Anki cards from S2 | Self-study | M1 | 5 cards |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-13:45 | Hire A: weekly 1:1 (agenda in docs/03-check-ins-and-scorecards.md) | Manager | M0 | W2 plan agreed; actions noted |
| 13:00-13:45 | Hire B: compare two items' cost elements in the extract; draft one question on how the duty rate in standard cost is set and maintained | Self-study | M5C | Comparison note; question logged |
| 13:45-14:30 | Hire B: weekly 1:1 | Manager | M0 | W2 plan agreed; actions noted |
| 13:45-14:30 | Hire A: re-read the e2open section of the trade systems primer; write 3 Anki cards | Self-study | M2 | 3 cards |
| 14:30-16:00 | Analytics: write "what I would do differently" for Exercises 1-2, then read Exercise 3 and list its data questions. Hire B: if this is done early, start Exercise 3 | Self-study | M3 | Retro note; Exercise 3 questions |
| 16:00-16:45 | Catch-up buffer: finish anything left from your W1 plan | Self-study | M0 | W1 plan items closed or carried |
| 16:45-17:00 | Put the final W2 plan in Planner | Self-study | M0 | W2 plan in Planner |

## Week 2 (Mon 10/26 - Fri 10/30)

Week focus: M1 Canada, Mexico, USMCA and classification basics; M2 AS400 trade data flow; M3 analytics Exercises 3-4; M4 intake; M5R and M5C first real-item shadow; M6 tool inventory; the first teach-back.

### Day 6 - Mon 10/26

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-08:15 | Anki daily review | Self-study | M1 | Reviews done |
| 08:15-08:30 | Monday confirm: walk the Manager through your W2 plan and agree the week's top-3 | Manager | M0 | Confirmed W2 plan |
| 08:30-10:00 | Read the Canada sections of docs/primers/customs-trade-compliance-primer.md: CBSA, CARM, the CAD, the Customs Tariff, the broker's role (pre-read for S3) | Self-study | M1 | Canada questions in the question log |
| 10:00-12:00 | Analytics Exercise 3 | Self-study | M3 | Exercise 3 file in progress |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-14:30 | Read the Mexico sections of the customs primer: ANAM, the agente aduanal, the pedimento, TIGIE, IMMEX, Anexo 24 and Anexo 30 (formerly Anexo 31) concepts | Self-study | M1 | Mexico questions in the question log |
| 14:30-15:00 | Hire A: business orientation II with the Manager. Open questions from your business map; who sends Research requests and why | Manager | M0 | Updated business map; stakeholder list |
| 14:30-15:00 | Hire B: trace one item from PO price to standard cost to receipt in the sanitized extracts | Self-study | M5C | One-item trace note |
| 15:00-16:45 | Hire A: track pre-read. docs/templates/domain/tariff-impact-brief.md, docs/primers/current-tariff-landscape.md, and the sanitized Tariff-Impact example | Self-study | M5R | 5 questions for Wednesday's shadow |
| 15:00-16:45 | Hire B: track pre-read. docs/templates/domain/tariff-impact-model-guide.md, the sanitized Tariff-Impact example, and docs/templates/domain/standard-cost-update-checklist.md | Self-study | M5C | 5 questions for Wednesday's shadow |
| 16:45-17:00 | Daily wrap | Self-study | M0 | Top-3 for Tue |

### Day 7 - Tue 10/27

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-08:15 | Anki daily review | Self-study | M1 | Reviews done |
| 08:15-09:00 | Pre-read for S3: on the sanitized CAD and pedimento [COMPANY], find the same 10 fields you found on the 7501 | Self-study | M1 | Field comparison started |
| 09:00-10:30 | S3, Canada and Mexico customs: CBSA, CARM and the CAD, release vs accounting, the Customs Tariff. Mexico: ANAM, the agente aduanal, the pedimento, TIGIE (8-digit fracción plus 2-digit NICO), IMMEX and Anexo 24 and 30 (formerly 31) concepts. How our brokers in each country get our data | Senior | M1 | Comparison table started |
| 10:30-12:00 | Finish a US/CA/MX comparison table (authority, filer, declaration, tariff schedule and digits, portal, main programs); write 5 Anki cards | Self-study | M1 | Comparison table; 5 cards |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-14:30 | AS400 trade data-flow walkthrough: where item trade data (HTS per country, origin, USMCA qualification) is created and maintained; how it reaches the brokers in US/CA/MX and what comes back; Oracle touchpoints (items, POs, receipts, costs); known pain points; which flows e2open will replace | Manager | M2 | As-is data-flow sketch |
| 14:30-16:00 | Redraw the data flow using docs/templates/bsa/03-process-map-as-is-to-be.md. List 5 data elements in the table in Section 7.3 of docs/primers/trade-systems-gtm-e2open-primer.md (data element, system of record, copied to, owner, known issues). The field-level spec in docs/templates/bsa/04-data-mapping-spec.md comes in W7 | Self-study | M2 | Data-flow v1; 5-row mini data map |
| 16:00-16:45 | Finish Exercise 3 and post it to OneNote 07 Analytics for Thursday's review | Self-study | M3 | Exercise 3 posted |
| 16:45-17:00 | Daily wrap | Self-study | M0 | Top-3 for Wed |

### Day 8 - Wed 10/28

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-08:15 | Anki daily review | Self-study | M1 | Reviews done |
| 08:15-08:30 | Stand-up (hires only); send your batched questions for the Senior's 15:15 office hours by 12:00 | Hires | M0 | Blockers posted |
| 08:30-10:00 | Classification basics: read the classification section of the customs primer (HS structure, national digits, General Rules of Interpretation 1-6). Classify the 5 sanitized practice items using hts.usitc.gov and CBP's CROSS rulings search (rulings.cbp.gov); record the rule you relied on | Self-study | M1 | 5-item classification worksheet for Thursday |
| 10:00-12:00 | Hire A: shadow a real Research item with [COMPANY: current Research process runner]. Cover the trigger, sources, legal scope, matching HTS and countries to our items, the brief, the review and the handoff | Shadow | M5R | Shadow notes: steps, sources, decisions, handoff |
| 10:00-12:00 | Hire B: shadow a real standard cost input or variance question with [COMPANY: current Standard Cost process runner or Finance cost accountant]. Cover the question, the data pulled, the calculation, the review and the answer | Shadow | M5C | Shadow notes: steps, data, checks, answer |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-13:45 | BSA craft intro: logging intake (docs/templates/bsa/01-intake-request.md), writing a Jira story with acceptance criteria (docs/templates/bsa/07-jira-epic-story.md), when a change request is needed (docs/templates/bsa/06-change-request.md) | Manager | M4 | Each hire drafts the intake record for their shadowed item |
| 13:45-15:00 | Write up your shadow: the intake record, a Jira story, and the as-is steps, kept as raw material for your future SOP (docs/templates/knowledge/process-sop.md) | Self-study | M4 | Intake, story and as-is steps posted |
| 15:00-15:15 | Hire A: USMCA oral test-out with the Senior, without notes: self-check questions 14-18 in Section 16 of docs/primers/customs-trade-compliance-primer.md. 4 of 5 correct is a pass: skim primer 10.2-10.5 in W3 and spend the saved time on 10.6, 10.9 and the tariff-landscape sources | Senior | M1 | Result in the question log and the W3 plan |
| 15:00-15:15 | Hire B: start Analytics Exercise 4 | Self-study | M3 | Exercise 4 started |
| 15:15-15:30 | Senior office hours: batched questions | Senior | M1 | Answers recorded in the question log |
| 15:30-16:45 | Analytics Exercise 4 | Self-study | M3 | Exercise 4 in progress |
| 16:45-17:00 | Daily wrap | Self-study | M0 | Top-3 for Thu |

If no live item is in progress on Wed 10/28, the same person walks through the most recent completed item (its Jira history and files) instead. The output stays the same.

### Day 9 - Thu 10/29

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-08:15 | Anki daily review | Self-study | M1 | Reviews done |
| 08:15-10:00 | Finish Analytics Exercise 4 and post it to OneNote 07 Analytics | Self-study | M3 | Exercise 4 posted |
| 10:00-11:00 | Custom tools kickoff: what we know about the 10+ tools. Split them: Hire A takes the tools nearest Research, classification and origin/USMCA; Hire B takes the tools nearest cost, landed cost, cost extracts and reports. Walk through the Tool Inventory tab in the trackers workbook and docs/templates/knowledge/tool-doc.md | Manager | M6 | Every tool row has an assigned learner |
| 11:00-12:00 | Start the inventory: for each of your tools, fill in purpose, business users, stack, where it lives, run frequency and knowledge holder. Do not run any tool that writes data | Self-study | M6 | First rows filled in |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-14:30 | S4, USMCA origin and classification basics: origin criteria (wholly obtained, tariff shift, regional value content), the certification of origin and its minimum data elements, importer, exporter and producer obligations, recordkeeping and verification. Then work the General Rules of Interpretation on 2 of the 5 worksheet items | Senior | M1 | Corrected worksheet; USMCA one-pager |
| 14:30-15:00 | Analytics review: the Senior reviews Exercises 1-3 against the answer key, which stays with the trainers (approach, Power Query or SQL hygiene, how the result was checked). Exercise 4 is reviewed in W3 | Senior | M3 | Fix list per hire |
| 15:00-16:00 | Teach-back prep (docs/templates/knowledge/teach-back.md): 10 minutes outside your own track. Hire A: "Our trade data flow: AS400, brokers, Oracle". Hire B: "US vs Canada vs Mexico: who files what". The Manager may swap topics | Self-study | M0 | Teach-back outline |
| 16:00-16:45 | Hire A: classification stretch. Add a kit or set item to the worksheet (GRI 3(b)) and write down its USMCA origin question | Self-study | M1 | Kit item added |
| 16:00-16:45 | Hire B: analytics stretch. Do the Hire B stretch of Exercise 3 in docs/analytics/practice-exercises.md on the sanitized standard cost extract: implied duty rate per item against the HTS general rate (read-only; no system writes) | Self-study | M3 | One-page finding |
| 16:45-17:00 | Daily wrap | Self-study | M0 | Top-3 for Fri |

### Day 10 - Fri 10/30

AM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 08:00-08:15 | Anki daily review | Self-study | M1 | Reviews done |
| 08:15-09:30 | Continue the tool inventory | Self-study | M6 | More rows filled in |
| 09:30-10:00 | Rehearse your teach-back once, out loud and timed | Self-study | M0 | Fits in 10 minutes |
| 10:00-10:30 | First Friday teach-back: 10 minutes each plus 5 minutes of feedback each | Manager | M0 | Feedback and corrections noted in OneNote |
| 10:30-11:30 | Friday self-report and W3 weekly plan; send to the Manager by 11:30 | Self-study | M0 | Self-report and W3 plan sent |
| 11:30-12:00 | Fix any errors found in the teach-back in your notes and cards | Self-study | M1 | Notes and cards corrected |

PM

| Time | Activity | Lead | Module | Output |
| --- | --- | --- | --- | --- |
| 13:00-13:45 | Hire A: weekly 1:1 | Manager | M0 | W3 plan agreed; actions noted |
| 13:00-13:45 | Hire B: read Section 5 (e2open) of docs/primers/trade-systems-gtm-e2open-primer.md; write 3 Anki cards | Self-study | M2 | 3 cards |
| 13:45-14:30 | Hire B: weekly 1:1 | Manager | M0 | W3 plan agreed; actions noted |
| 13:45-14:30 | Hire A: tool inventory | Self-study | M6 | Rows filled in |
| 14:30-16:00 | Hire A: set up research monitoring. Subscribe to CBP CSMS messages and Federal Register email alerts as described in docs/primers/current-tariff-landscape.md; log one recent notice as a practice research item | Self-study | M5R | Subscriptions active; 1 practice item logged |
| 14:30-16:00 | Hire B: PPV. Using the sanitized PPV example, explain 3 variances in plain words (price, freight, duty) | Self-study | M5C | 3 variance explanations |
| 16:00-16:45 | Catch-up buffer: finish anything left from your W2 plan | Self-study | M0 | W2 plan items closed or carried |
| 16:45-17:00 | Put the final W3 plan in Planner | Self-study | M0 | W3 plan in Planner |

## Where Hire A and Hire B differ

| Topic | Hire A (Research) | Hire B (Standard Cost) |
| --- | --- | --- |
| Business orientation | Full: Purchasing/Logistics shadow (Tue 10/20), deck self-study (Wed 10/21), two Manager sessions (Thu 10/22, Mon 10/26); stakeholder intro meetings follow in W3-W4 | Refresher only: a 30-minute skim (Tue 10/20); the other slots go to Oracle cost data |
| USMCA | Oral test-out Wed 10/28 (prior exposure) | No test-out; target is proficiency 1 at day 30 |
| Oracle cost data | Not in W1-W2 beyond the landscape and data-flow sessions | Every spare slot: cost elements, standard cost checklist, one-item trace, PPV |
| Finance contact | None in W1-W2 | Shadow with Finance (Thu 10/22) |
| Track pre-read and shadow | Tariff-Impact Brief, tariff landscape, real Research item | Tariff-Impact Model guide, cost checklist, real cost or variance item |
| Stretch work | Kit/BOM origin and GRI 3(b), building on prior USMCA and BOM exposure | Analytics on the real cost extract, since data comes quickly |
| Tool split | Research, classification and origin tools | Cost, landed-cost and extract or report tools |

## Week 2 exit check (Fri 10/30)

Review in the Friday 1:1s. Anything unchecked goes in the W3 plan with a date.

- ☐ Can explain the US entry flow, from 3461 to liquidation, without notes.

- ☐ US/CA/MX comparison table and the 5-item classification worksheet are posted and corrected.

- ☐ Systems landscape v1 and AS400 trade data-flow v1 are posted.

- ☐ Analytics Exercises 1-4 are posted, and Exercises 1-3 have had the Senior's feedback.

- ☐ Shadow write-up done: intake record, Jira story and as-is steps.

- ☐ Every row in the Tool Inventory tab has a learner, and each hire has filled in at least the basic fields for their tools.

- ☐ First teach-back done and feedback recorded.

- ☐ Anki reviewed on 9 of 10 days; at least 15 of their own cards drafted.

- ☐ Question log in daily use, and two Friday self-reports sent on time.

- ☐ Every access item due by W2 has status Verified, or has an escalation logged.

## Trainer hours

Counting rule: a session that both hires attend counts once. A row with a "Hire A:" or "Hire B:" prefix counts on its own. Stand-ups are hire-only and cost no trainer time. Shadow hosts and HR are not in the trainer budget; see "Other people's time" below. Only rows in the day tables above are counted. These line items match the W1 and W2 rows of the trainer-load table in docs/01-30-60-90-plan.md Section 5. The gap up to the cap is the Manager's async review and buffer time (self-reports, notes, cards, access chasing, next-week prep).

### Week 1 line items

| Day | Session | Manager h | Senior h |
| --- | --- | --- | --- |
| Mon 10/19 | Welcome and 30/60/90 plan | 1.00 | 0.00 |
| Mon 10/19 | Meet the Senior | 0.00 | 0.25 |
| Mon 10/19 | Day-1 wrap | 0.25 | 0.00 |
| Tue 10/20 | Trade systems landscape | 1.50 | 0.00 |
| Wed 10/21 | Ways of working: Jira, Planner, time management | 1.00 | 0.00 |
| Wed 10/21 | S1: US customs fundamentals I | 0.00 | 1.50 |
| Thu 10/22 | Hire A business orientation | 0.75 | 0.00 |
| Thu 10/22 | Data landscape tour | 0.00 | 0.50 |
| Thu 10/22 | Senior office hours | 0.00 | 0.50 |
| Fri 10/23 | S2: US customs fundamentals II | 0.00 | 1.50 |
| Fri 10/23 | Hire A 1:1 | 0.75 | 0.00 |
| Fri 10/23 | Hire B 1:1 | 0.75 | 0.00 |
| W1 total |  | 6.00 | 4.25 |

### Week 2 line items

| Day | Session | Manager h | Senior h |
| --- | --- | --- | --- |
| Mon 10/26 | Monday confirm | 0.25 | 0.00 |
| Mon 10/26 | Hire A business orientation II | 0.50 | 0.00 |
| Tue 10/27 | S3: Canada and Mexico customs | 0.00 | 1.50 |
| Tue 10/27 | AS400 trade data-flow walkthrough | 1.50 | 0.00 |
| Wed 10/28 | BSA craft intro: intake and Jira stories | 0.75 | 0.00 |
| Wed 10/28 | Hire A USMCA test-out and Senior office hours | 0.00 | 0.50 |
| Thu 10/29 | Custom tools kickoff | 1.00 | 0.00 |
| Thu 10/29 | S4: USMCA origin and classification basics | 0.00 | 1.50 |
| Thu 10/29 | Analytics review | 0.00 | 0.50 |
| Fri 10/30 | First teach-back | 0.50 | 0.00 |
| Fri 10/30 | Hire A 1:1 | 0.75 | 0.00 |
| Fri 10/30 | Hire B 1:1 | 0.75 | 0.00 |
| W2 total |  | 6.00 | 4.00 |

### Totals vs capacity

| Week | Manager scheduled h | Manager cap h | Manager review and buffer h | Senior scheduled h | Senior cap h |
| --- | --- | --- | --- | --- | --- |
| W1 (10/19-10/23) | 6.00 | 8.00 | 2.00 | 4.25 | 4.50 |
| W2 (10/26-10/30) | 6.00 | 8.00 | 2.00 | 4.00 | 4.50 |

Both weeks fit. The Senior has 0.25 h (W1) and 0.50 h (W2) of headroom under the 4.5 h planning cap, so do not fill it. The Senior's prep for S1-S4 (about 1 h) is done in the week of Mon 10/12, before the hires start, so it is not in these totals.

### If you or the Senior host a shadow

The table above assumes the Wed 10/28 shadows are hosted by someone other than the Manager or the Senior.

- If the Manager runs Research and Standard Cost today: cut each shadow to 60 minutes and run them back to back (Hire A 10:00-11:00, Hire B 11:00-12:00). During that hour, the hire who is not shadowing starts Analytics Exercise 4 (pulled forward from 15:30). Move Hire A's business orientation II (Mon 10/26) to self-study. W2 Manager total becomes 6.00 - 0.50 + 2.00 = 7.50 h, which is still under 8.

- If the Senior hosts the Research shadow: cap it at 45 minutes and cut the Wed 15:00 slot to the 15-minute test-out (questions go to S4). W2 Senior total becomes 4.00 + 0.75 - 0.25 = 4.50 h, exactly at the cap.

## Other people's time (not in the trainer budget)

| Who | Hire | When | Hours |
| --- | --- | --- | --- |
| [COMPANY: HR and IT onboarding] | Both | Mon 10/19 08:00-12:00 | 4.00 |
| [COMPANY: Purchasing or Logistics contact] | Hire A | Tue 10/20 10:30-12:00 | 1.50 |
| [COMPANY: Finance cost accountant] | Hire B | Thu 10/22 10:00-11:00 | 1.00 |
| [COMPANY: current Research process runner] | Hire A | Wed 10/28 10:00-12:00 | 2.00 |
| [COMPANY: current Standard Cost process runner or Finance cost accountant] | Hire B | Wed 10/28 10:00-12:00 | 2.00 |
| [COMPANY: stakeholder group contacts] | Hire A | W3-W4, one 30-minute intro meeting per group | 0.50 each |

## If something moves

- A trainer session is cancelled: swap it with a self-study block in the same week (move the self-study earlier, the session later). Don't drop it. If it can't happen this week, it goes first in next week's plan and the Manager updates the totals.

- Access is late: follow the fallback table in docs/04-access-request-checklist.md. The session still runs on the trainer's screen.

- A hire finishes early: go to the next exercise in docs/analytics/practice-exercises.md, or write more cards from the question log. Don't start real work items before W3 without the Manager's OK.

- A hire falls behind: the 16:00-16:45 Friday buffer comes first. After that, carry it to the next week's plan; the Manager decides what drops.

- A live tariff action lands during W1-W2: in W1-W2 the trainer is always maker. Hire A shadows it (in place of the Wed 10/28 slot if it overlaps) and writes after-action notes; see the note before the handling in scenario 1 of docs/05-time-management.md.