# Program at a Glance: BSA New Hires

Last updated: 2026-10-17 · Owner: BSA Manager

- Purpose: a short summary of the 90-day program for the two new BSAs. The full plan is docs/01-30-60-90-plan.md; if this page and the plan ever differ, the plan wins.

- Who uses it: BSA Manager (owner), Senior BSA (co-trainer), Hire A (Research track), Hire B (Standard Cost track).

- When: Manager and Senior before Day 1 (Mon 2026-10-19); hires at the Day-1 welcome (Mon 10/19 13:00). Everyone: check the current week's roadmap row every Monday.

## Key dates

| Milestone | Date | Week | Notes |
| --- | --- | --- | --- |
| Day 1 | Mon 2026-10-19 | W1 | Orientation, access checks, first sessions |
| First teach-back | Fri 2026-10-30 | W2 | First weekly Friday teach-back (15 min per hire) |
| Day-30 review | Wed 2026-11-18 | W5 | 60 min per hire; knowledge check and evidence due Mon 11/16 |
| Exports items start | Mon 2026-11-23 | W6 | 3-day week: Thanksgiving Thu 11/26; Fri 11/27 assumed off ([COMPANY: confirm holiday calendar]) |
| Day-60 review | Fri 2026-12-18 | W9 | 60 min per hire, with an owned-tool demo; evidence due Wed 12/16 |
| Reporting items start | Mon 2026-12-21 | W10 | Reduced capacity (Christmas) |
| e2open kickoff | Expected W12 (1/4–1/8) | W12 | [COMPANY: confirm kickoff date] |
| Day-90 review | Fri 2027-01-15 | W13 | 60 min per hire; ownership decision; evidence due Wed 1/13 |

## The two tracks

- Hire A, Research (M5R): tariff and regulatory change research, ad-hoc investigations, modeling new tariff actions before they take effect. Checker: Senior or Manager.

- Hire B, Standard Cost (M5C): duty and landed-cost inputs to Oracle standard costs, the cost update cycle with Finance, tariff impact on cost and margin, PPV. Checker: Manager, plus Finance sign-off.

- Both: exports backlog items from W6 (M7), reporting backlog items from W10 (M8), drawback exposure only (M9; the Senior keeps it).

- Shared modules for both: M0 orientation, M1 customs, M2 trade systems, M3 data and analytics (with analytics depth in W7–W9: KPI design, star-schema model, DAX measures, variance statistics), M4 BSA fundamentals (W2–W3) and craft, M6 custom tools, M10 e2open, and three newer modules: M11 Copilot Chat for BSA work (W1 onward), M12 data platform (team database, SSMS, DBeaver on Oracle EBS read-only, Power BI, Power Automate, Power Apps, the remote server; W1–W6, then ongoing) and M13 SDLC and change delivery (W5–W6, applied in W8 and on e2open). Their self-study comes out of the existing self-study time.

## Trainers and weekly capacity

- BSA Manager: 8 h a week for both hires (about 5 h in W6, 4 h in W10 and W11). The only trainer for AS400 and the custom tools; also orientation, Oracle touchpoints, BSA fundamentals and craft, Copilot Chat rules, the data platform walkthrough, SDLC coaching on the owned tool, track coaching, 1:1s, reviews.

- Senior BSA: 4–5 h a week, planned at no more than 4.5 h (about 3 h in W6, 2.5 h in W10 and W11). Customs and trade compliance, data and analytics, exports, reporting, drawback; not AS400 or the custom tools.

- Each hire: about 40 h a week, about 5–8 h guided (about 9–10 h in W1–W2, about 5 h in W10–W13); the rest is structured self-study, shadowing, real low-risk work and documentation.

## Standard week (W3 onward)

Every recurring session from W3 sits in one of these slots ([COMPANY: confirm slots against core hours]). W1–W2 run day by day from docs/02-weeks-1-2-schedule.md.

| Day and time | Session | Who | Weeks |
| --- | --- | --- | --- |
| Mon 08:15–08:30 | Monday confirm | Manager, both hires | Every week |
| Tue–Fri 08:15–08:25 | Stand-up: top-3 and blockers; blockers go to the Manager in Teams | Both hires, no trainer | Every week |
| Tue 09:00–10:30 | Senior session 1 | Senior, both hires | Every week (the only Senior session in W6, W10, W11) |
| Tue 13:00–14:00, 14:00–15:00 | Track coaching: Hire A, then Hire B | Manager, one hire | W3, W4, W7, W8 |
| Wed 10:00–11:00 | Manager shared session (M2, M4, M10, drill debrief; in W4 also the 15-minute M11 Copilot use-log review; in W12 the kickoff debrief, on the day after the kickoff) | Manager, both hires | W3, W4, W7, W8, W9, W12 |
| Wed 13:00–14:00, 14:00–15:00 | Tool-ownership coaching: Hire A, then Hire B | Manager, one hire | W4, W5–W9 |
| Wed 15:00–15:30 | Senior office hours (questions in by 12:00; in W3 the slot is small-analysis scoping, 15 minutes for Hire B, then 15 for Hire A) | Senior, both hires | Not W5, W6, W9, W10, W11 |
| Thu 10:00–11:00 | Second Manager shared session | Manager, both hires | W3 |
| Thu 13:00–14:30 | Senior session 2 (W4: 13:00–14:00 small-analysis SQL review) | Senior, both hires | Not W6, W10, W11 |
| Fri 10:00–10:30 | Teach-back | Manager, both hires | Not W6, W9, W11, W13 |
| Fri 11:30 | Friday self-report due (docs/03-check-ins-and-scorecards.md Section 5) | Both hires | Every week (holiday Fridays: see below) |
| Fri 13:00–13:45, 13:45–14:30 | 1:1: Hire A, then Hire B (30 minutes each in W5, W6, W9–W11, W13) | Manager, one hire | Every week (holiday Fridays: see below) |
| Review days 08:30–09:30, 09:45–10:45 | Milestone review: Hire A, then Hire B (Wed 11/18, Fri 12/18, Fri 1/15) | Manager, one hire | W5, W9, W13 |

Holiday Fridays: when Friday is not a working day (W6 Fri 11/27, assumed off; W10 Fri 12/25; W11 Fri 1/1), the Friday self-report, the 1:1s and the teach-back (W10 only; there is none in W6 or W11) move to the last working day of that week, at the Friday times ([COMPANY: confirm holiday calendar]). In W6 that is Wed 11/25, and the 1:1s run 15:00–15:30 and 15:30–16:00, after tool coaching. The 1:1s are never skipped in these weeks.

## Roadmap W1–W13

| Week | Dates | Both hires | Hire A (Research) | Hire B (Std Cost) |
| --- | --- | --- | --- | --- |
| W1 | 10/19 – 10/23 | M0 orientation; M1 US customs; M2 systems landscape; M3 Exercises 1–2; M11 Copilot setup and rules; M12 safe-use rules (before any SSMS or DBeaver use) and the data landscape tour | Business orientation | Business overview refresher; Oracle cost data |
| W2 | 10/26 – 10/30 | M1 Canada, Mexico, USMCA, classification; M2 AS400 data flow; M12 data platform walkthrough; M4 BSA fundamentals; M6 inventory; Copilot use log starts; first teach-back | Research shadow; USMCA test-out Wed 10/28 | Cost or variance shadow |
| W3 | 11/2 – 11/6 | M1 valuation, USMCA origin; reading a tariff action; M2 Oracle and broker data; M4 intake with stakeholder list and elicitation plan by Fri 11/6; SSMS lab starts | M5R kickoff; stakeholder intros; scope the analysis | M5C kickoff; scope the analysis |
| W4 | 11/9 – 11/13 | M1 IMMEX, Anexo 24 and 30; M4 process mapping; classification worksheet due Wed 11/11; Copilot use-log review Wed 11/11; SSMS lab reviewed Thu 11/12 | Brief outline; small analysis | Landed cost for 5 items; analysis due Fri 11/13 |
| W5 | 11/16 – 11/20 | Knowledge check Mon 11/16; day-30 review Wed 11/18; M7 exports overview; M13 SDLC primer Parts 1–4; Power Platform lab | Weekly tariff-landscape upkeep starts | Cost cycle walkthrough |
| W6 | 11/23 – 11/25 (3 days) | No new core content; exports item 1; supervised owned-tool run; test copy set up; SDLC applied to the owned tool; server lab | Tool doc started | Tool doc started |
| W7 | 11/30 – 12/4 | Joint tariff drill part 1; M3 Power BI and warehouse depth; Exercise 9 (KPI design); M4 data mapping and UAT | Brief for a real recent action (A60-1) | PPV analysis and SOP draft (B60-3) |
| W8 | 12/7 – 12/11 | Drill part 2 (checker demo); test-copy tool change (change request with environments, test evidence and rollback); Exercise 10 (star schema); exports item 2 | Model handoff; ad-hoc investigation | $ impact model; dry-run input file |
| W9 | 12/14 – 12/18 | Day-60 review Fri 12/18; M10 prep; M8 report inventory; Exercise 11 (variance statistics) by Thu 12/17 | Start Research as-is map | Start Standard Cost as-is map |
| W10 | 12/21 – 12/25 (about 50%) | Christmas week; M8 reporting handoff; as-is drafting | Monitor for an A90-1 action | Year-end cycle prep if scheduled |
| W11 | 12/28 – 1/1 (about 50%) | New Year week; M9 drawback overview; data-map drafting | Research data-map draft | Standard Cost data-map draft |
| W12 | 1/4 – 1/8 | e2open kickoff (expected); M9 drawback shadow; second tool doc | Research cycle as maker (or fallback) | Cost cycle as maker |
| W13 | 1/11 – 1/15 | Day-90 review Fri 1/15; final as-is doc and data map | Publish Research SOP v1.0 | Reconciliation tie-out; publish SOP v1.0 |

## The bar at day 30, 60 and 90

Must criteria decide the outcome; Should criteria are expected (a Should rated 1 or 2 gets a catch-up action in the next 1:1) but do not change it; Stretch criteria never block "on track". On track = every Must rated 3 or 4. All counts are minimums. Full criteria and evidence: plan Section 4.

### Day 30 (Wed 2026-11-18)

Hire A (Research)

- A30-1 to A30-3: 80% or more on the knowledge check; 8 of 10 items right at 6 digits; USMCA at proficiency 2.

- A30-4 to A30-6: data flow drawn from memory; Exercises 1–6 and one real analysis; sources found in 60 minutes or less.

- A30-7 to A30-9: 20 cards, 1 SOP draft, 3 teach-backs; Jira and self-reports current; stakeholder map.

- A30-11 (Must): data platform safe-use rules followed; SSMS lab finished and reviewed. A30-12, A30-13 (Should): 5 reviewed Copilot uses; stakeholder list and elicitation plan on the small analysis intake.

Hire B (Standard Cost)

- B30-1 to B30-3: same knowledge check and classification bar as Hire A; USMCA and IMMEX at proficiency 1.

- B30-4 to B30-6: where duty, freight and fees enter Oracle cost data; analysis by Fri 11/13; landed cost for 5 items.

- B30-7 to B30-9: same documenting and Jira bar as Hire A; queries item standard cost without help.

- B30-11 to B30-13: same data platform Must and the same two Should criteria as Hire A.

### Day 60 (Fri 2026-12-18)

Hire A (Research)

- A60-1, A60-2: brief for a real recent action, primary source for every claim; WHAT handed to Hire B, no $.

- A60-3, A60-4: one ad-hoc investigation end to end; owns [COMPANY: tool closest to Research] (one end-to-end run, either supervised in production or on a test copy; a change request naming environments, test evidence and rollback; the tool's platform path in its doc).

- A60-5 to A60-7: 1 exports item; core skills at 2, "find and read primary sources" at 3; 50 cards, 6 teach-backs, 2 SOPs, 1 tool doc.

- A60-9 (Should): analytics Exercises 9 and 10 reviewed, Exercise 11 submitted.

Hire B (Standard Cost)

- B60-1, B60-2: $ impact modeled from a Tariff-Impact Brief; cost cycle input file (real cycle or dry run).

- B60-3, B60-4: PPV for one closed period, top 10 variances by driver; owns [COMPANY: name of std-cost tool] (one end-to-end run, either supervised in production or on a test copy; a change request naming environments, test evidence and rollback; the tool's platform path in its doc).

- B60-5 to B60-7: same exports and documenting bar as Hire A; core skills at 2, "build item landed cost" at 3.

- B60-9 (Should): same analytics depth bar as Hire A.

### Day 90 (Fri 2027-01-15)

Hire A (Research)

- A90-1: Research cycle end to end as maker on a live action (5 or more business days' lead) or the plan's Section 7 fallback.

- A90-2 to A90-4: e2open as-is doc and data map for Research, reviewed; Research SOP v1.0 published.

- A90-5 to A90-7: 2 exports items in total; core skills at 3; 80 cards, 9 teach-backs, 3 SOPs, 2 tool docs.

- A90-10 (Should): 3 of your own entries in the team Copilot prompt library, each reviewed by the Manager.

Hire B (Standard Cost)

- B90-1: one cost update cycle as maker (live, parallel run or interim update); Finance and checker sign-off before any Oracle load; reconciliation ties out.

- B90-2 to B90-4: e2open as-is doc and data map for Standard Cost, reviewed; SOP v1.0 published.

- B90-5 to B90-7: same exports and documenting bar as Hire A; core skills at 3.

- B90-10 (Should): same Copilot prompt library bar as Hire A.

## The rules

- Boundary: Research owns the WHAT (action, legal scope, items in scope, HTS codes, countries, rates, effective dates, stacking, exclusions, sources) and hands it off in a Tariff-Impact Brief. Standard Cost owns the $ (landed cost and margin, the Oracle cost update, variances) and never decides scope. One shared Tariff-Impact Model.

- Maker-checker: every standard cost update and every tariff model released to the business gets a documented Senior or Manager review before release, also after day 90. Hire B never loads to Oracle EBS production without Finance and checker sign-off.

- Live tariff urgency (business days to effective date): under 5 or business-critical, a trainer is maker and the hires shadow and draft a parallel practice brief or model; 5–15, the hire is maker with a 15-minute daily checkpoint, and the checker reviews each draft on the same business day it is submitted (from the checker's review or buffer time), with nothing released before that review; over 15, the hire is maker on the normal cycle. In W1–W2 the trainer is always maker.

- Brokers and counsel: before the day-60 review, no direct contact with a customs broker, agente aduanal or trade counsel; questions go through the Senior (or the Manager). After day 60, with the Senior's agreement, email the broker with the Senior copied.

- Data platform: your personal login for all interactive work, never the service account; Oracle EBS read-only; loads only into [COMPANY: sandbox or staging schema in the team database]; no schema changes; no production write before the day-60 review (docs/primers/data-platform-primer.md Part 1).

- Copilot Chat: its output is a draft; maker-checker and primary sources still apply, and Copilot is never cited as a source (docs/primers/copilot-chat-guide.md Part 2).

## Where things live

- OneNote: the program pages and the hires' diagrams, analyses, SOPs and Copilot use logs (only Reviewed and Published docs in the shared section). The team Copilot prompt library is a page in [COMPANY: team OneNote section for the prompt library], where each entry carries its own status, such as Proposed or Reviewed (docs/templates/knowledge/copilot-prompt-library.md).

- Onboarding folder ([COMPANY: team onboarding folder on SharePoint/Teams]): the trackers workbook BSA-Onboarding-Trackers.xlsx (Skills, Knowledge Topics, Glossary, Tool Inventory tabs), the team Anki deck BSA-Onboarding.apkg, Tariff-Impact-Model-Template.xlsx, Practice-Data.xlsx, Word versions of these pages.

- Anki: only the cards you write count toward 20, 50 and 80; the team deck does not.

- Trainer-only ([COMPANY: trainer-only location]): the analytics answer key and data generator. The hires do not get the key before the day-30 review; after it, the Manager decides whether to share the key, without its Exercise 9–11 sections. The generator and those sections stay trainer-only until the day-60 review.